## Template
THE GTM LEAD ¦ TEMPLATE
B2B go-to-market launch tracker
Each row is one verifiable deliverable with an owner, an approver, proof and a launch gate. The example rows are for HarborDesk, a fictional B2B SaaS product introducing a new support workflow. Replace the names and relative dates with your own launch.
Grey italic text is an example. Replace it with your own content.
LAUNCH TRACKER (12 COLUMNS, 8 EXAMPLE ROWS)
Workstream | Deliverable | ICP | Owner | Approver | Due date | Dependency | Proof link | Status | Launch gate | KPI | Next action
Research | ICP interview synthesis | Support ops leads | Product marketing | launch lead | T-35 | Interviews complete | Research summary | Approved | ICP confirmed | Qualified interview themes | Share disqualifiers
Positioning | Positioning and claim sheet | Support ops leads | Product marketing | Product lead | T-28 | ICP synthesis | Approved messaging doc | Approved | Messaging approved | Message comprehension | Lock claims
Packaging | Price and eligibility FAQ | Support ops leads | Product | Finance lead | T-24 | Offer decision | Draft FAQ | In review | Pricing signed off | FAQ accuracy | Resolve exceptions
Demand | Segment landing page | Support ops leads | Growth lead | Product marketing | T-16 | Approved claims | Staging page | In progress | Page QA passed | Qualified visits | Test forms
Sales | Rep talk track and objection guide | Buying committee | Enablement lead | Sales lead | T-10 | Messaging approved | Training deck | In progress | Field readiness proven | Correct readiness answers | Run short check
Success | Existing-customer change notice | Customer admins | CS lead | Product lead | T-7 | Support policy | Draft notice | Blocked | Support ready | Notice delivery | Confirm impact
Operations | Go/no-go decision | All launch audiences | launch lead | Executive sponsor | T-2 | All critical gates | Decision record | Not started | Launch decision logged | Open critical blockers | Convene owners
Measurement | Funnel baseline and dashboard | Support ops leads | RevOps lead | launch lead | T-7 | Tracking specification | Dashboard link | In progress | Reporting ready | Qualified pipeline | QA attribution
STATUS VALUES
Done | Item
Not started
In progress
Blocked
In review
Approved